## Sheet1
ShopeeFood Clone Project - Risk management
ICT - HUST
Management of Software Development
Risk and Mitigation strategies
Risk ID | Risk description | Probability (High, Moderate, Low | Impact (High, Moderate, Low | Severity | Owner | Mitigation strategies
1 | Inadequate customer testing leads to delay in product release | High | High | Unacceptable | Project Manager | Ensure customer prepares test cases/quality checks and protect testing/quality assurance window. Raise risk immediately and raise issue if it is clear testing inadequate.
2 | Lack of communication, causing lack of clarity and confusion. | Moderate | Moderate | High | Project Manager | Write a communication plan which includes frequency, goal, and audience of each communication. Use most appropriate channel of communication e.g. make a call instead of sending email
3 | Operation in an unfamiliar software environment causes unforeseen problems | Moderate | Moderate | High | Project Manager | Choosing technical stack at the beginning of project and giving time to team members to learn and familiarize themselves with new technologies.
4 | Project schedule is not clearly defined or understood | Low | Moderate | Moderate | Project Manager | Hold scheduling meetings with the project team frequently so they understand the plan and likelihood of missed tasks is reduced.
5 | Unplanned work that must be accommodated | Low | High | Moderate | Project Manager | Attend project scheduling meetings. Check all plans and quantity surveys. Document all assumptions made in planning and communicate to the project manager before project kick off.
6 | Pressure to arbitrarily reduce task durations and/or run tasks in parallel which would increase risk of errors. | Low | High | Moderate | Project Manager | Share the schedule with Project Owner to reduce the risk of this happening. Explain the risks of the changes.
7 | Project conflicts are not solved in a timely manner | Low | Moderate | Moderate | Project Manager | Hold regular project team meetings and look out for conflicts. Review the project plan and requirements for potential areas of conflict.
8 | Added workload or time requirements because of new direction, policy, or statute | Low | Moderate | Moderate | Project Manager | No ability to reduce likelihood.
9 | Theft of materials, or intellectual property. | Low | High | Moderate | Project Manager | Follow security procedures, ensure Non-Disclosure Agreements (NDAs), & compliance certificates are in place. Verify all copyrights in project.
10 | Project purpose and need is not well-defined. | Low | Low | Low | Project Manager | Complete business specification if not already provided and ensure purpose is well defined on Project Charter.
11 | Meeting product’s size or speed constraints requires more time than expected, including time for redesign and reimplementation | Low | Moderate | Low | Project Manager | Make sure the design and requirements of system are introduce clearly to team members through meetings

## Sheet2
Risk Severity table |  | Probability
|  | 1 | 2 | 3
Impact | 1 | Low | Low | Moderate
| 2 | Moderate | High | High
| 3 | Moderate | High | Unacceptable
Risk Severity table |  | Probability
|  | 1 | 2 | 3
Impact | 1 | 1 | 1 | 2
| 2 | 2 | 3 | 3
| 3 | 2 | 3 | 4